## Sheet1
Page | Feature | API Name | Endpoint | Method | UI Time | API Time | DB Time | Notes
Login | Sign in form, validation, redirect | auth.login | /api/v1/auth/login | POST | 15 min | 25 min | 15 min | token/session handling
Login | Logout | auth.logout | /api/v1/auth/logout | POST | 10 min | 15 min | 10 min | clear session/token
Login | Current user | auth.me | /api/v1/auth/me | GET | 10 min | 15 min | 10 min | user role and profile
Dashboard | KPI cards | dashboard.kpis | /api/v1/dashboard/kpis | GET | 25 min | 25 min | 20 min | aggregate queries
Dashboard | Asset class chart | dashboard.assetClassEmissions | /api/v1/dashboard/asset-class-emissions | GET | 25 min | 25 min | 20 min | grouped totals
Dashboard | Sector chart | dashboard.sectorEmissions | /api/v1/dashboard/sector-emissions | GET | 25 min | 25 min | 20 min | sector-wise sums
Dashboard | Top highest exposures | dashboard.topHighest | /api/v1/dashboard/top-exposures?type=highest | GET | 20 min | 25 min | 20 min | ranking query
Dashboard | Top lowest exposures | dashboard.topLowest | /api/v1/dashboard/top-exposures?type=lowest | GET | 20 min | 25 min | 20 min | ranking query
Dashboard | Yearly trend | dashboard.yearlyTrend | /api/v1/dashboard/yearly-trend | GET | 20 min | 25 min | 20 min | FY comparison
Loan Configuration | Business loan list | loanConfig.businessLoans.list | /api/v1/loan-config/business-loans | GET | 25 min | 25 min | 20 min | paginated list
Loan Configuration | Create business loan | loanConfig.businessLoans.create | /api/v1/loan-config/business-loans | POST | 25 min | 25 min | 25 min | validation + insert
Loan Configuration | Update business loan | loanConfig.businessLoans.update | /api/v1/loan-config/business-loans/:loanId | PUT | 25 min | 25 min | 25 min | update existing row
Loan Configuration | Delete business loan | loanConfig.businessLoans.delete | /api/v1/loan-config/business-loans/:loanId | DELETE | 15 min | 15 min | 15 min | soft delete recommended
Loan Configuration | CRE list | loanConfig.cre.list | /api/v1/loan-config/commercial-real-estate | GET | 20 min | 25 min | 20 min | read-only tab
Loan Configuration | Motor vehicle list | loanConfig.motorVehicle.list | /api/v1/loan-config/motor-vehicle | GET | 20 min | 25 min | 20 min | read-only tab
Loan Configuration | Mortgage list | loanConfig.mortgage.list | /api/v1/loan-config/mortgage | GET | 20 min | 25 min | 20 min | read-only tab
Loan Configuration | Import data | loanConfig.import | /api/v1/loan-config/import | POST | 25 min | 30 min | 20 min | CSV/Excel upload
Business Loan Capture | Capture list/filter | capture.businessLoans.list | /api/v1/captures/business-loans | GET | 30 min | 25 min | 25 min | search, status, date filters
Business Loan Capture | Record detail | capture.businessLoans.detail | /api/v1/captures/business-loans/:id | GET | 20 min | 25 min | 20 min | modal/detail payload
Business Loan Capture | Save draft | capture.businessLoans.saveDraft | /api/v1/captures/business-loans/:id/draft | POST | 20 min | 25 min | 25 min | draft status update
Business Loan Capture | Submit record | capture.businessLoans.submit | /api/v1/captures/business-loans/:id/submit | POST | 25 min | 25 min | 25 min | submit for approval
Business Loan Capture | Bulk approve | capture.businessLoans.bulkApprove | /api/v1/captures/business-loans/bulk-approve | POST | 20 min | 25 min | 25 min | batch update
Business Loan Capture | Bulk reject | capture.businessLoans.bulkReject | /api/v1/captures/business-loans/bulk-reject | POST | 20 min | 25 min | 25 min | batch update
Business Loan Capture | Audit history | capture.businessLoans.auditHistory | /api/v1/captures/business-loans/:id/audit-history | GET | 20 min | 25 min | 25 min | audit trail table
Business Loan Capture | Recalculate emissions | capture.businessLoans.recalculate | /api/v1/captures/business-loans/:id/recalculate | POST | 15 min | 25 min | 20 min | formula logic
Commercial RE Capture | Capture list/filter | capture.cre.list | /api/v1/captures/commercial-real-estate | GET | 30 min | 25 min | 25 min | filters + tabs
Commercial RE Capture | Record detail | capture.cre.detail | /api/v1/captures/commercial-real-estate/:id | GET | 20 min | 25 min | 20 min | selected row detail
Commercial RE Capture | Save draft | capture.cre.saveDraft | /api/v1/captures/commercial-real-estate/:id/draft | POST | 20 min | 25 min | 25 min | draft state
Commercial RE Capture | Submit record | capture.cre.submit | /api/v1/captures/commercial-real-estate/:id/submit | POST | 25 min | 25 min | 25 min | approval workflow
Commercial RE Capture | Bulk approve | capture.cre.bulkApprove | /api/v1/captures/commercial-real-estate/bulk-approve | POST | 20 min | 25 min | 25 min | batch action
Commercial RE Capture | Bulk reject | capture.cre.bulkReject | /api/v1/captures/commercial-real-estate/bulk-reject | POST | 20 min | 25 min | 25 min | batch action
Commercial RE Capture | Audit history | capture.cre.auditHistory | /api/v1/captures/commercial-real-estate/:id/audit-history | GET | 20 min | 25 min | 25 min | audit logs
Commercial RE Capture | Recalculate emissions | capture.cre.recalculate | /api/v1/captures/commercial-real-estate/:id/recalculate | POST | 15 min | 25 min | 20 min | emission formula
Motor Vehicle Capture | Capture list/filter | capture.motorVehicle.list | /api/v1/captures/motor-vehicle | GET | 30 min | 25 min | 25 min | tab/filter UI
Motor Vehicle Capture | Record detail | capture.motorVehicle.detail | /api/v1/captures/motor-vehicle/:id | GET | 20 min | 25 min | 20 min | edit modal data
Motor Vehicle Capture | Save draft | capture.motorVehicle.saveDraft | /api/v1/captures/motor-vehicle/:id/draft | POST | 20 min | 25 min | 25 min | draft save
Motor Vehicle Capture | Submit record | capture.motorVehicle.submit | /api/v1/captures/motor-vehicle/:id/submit | POST | 25 min | 25 min | 25 min | submit flow
Motor Vehicle Capture | Bulk approve | capture.motorVehicle.bulkApprove | /api/v1/captures/motor-vehicle/bulk-approve | POST | 20 min | 25 min | 25 min | batch approve
Motor Vehicle Capture | Bulk reject | capture.motorVehicle.bulkReject | /api/v1/captures/motor-vehicle/bulk-reject | POST | 20 min | 25 min | 25 min | batch reject
Motor Vehicle Capture | Audit history | capture.motorVehicle.auditHistory | /api/v1/captures/motor-vehicle/:id/audit-history | GET | 20 min | 25 min | 25 min | change log
Motor Vehicle Capture | Recalculate emissions | capture.motorVehicle.recalculate | /api/v1/captures/motor-vehicle/:id/recalculate | POST | 15 min | 25 min | 20 min | formula logic
Mortgage Capture | Capture list/filter | capture.mortgage.list | /api/v1/captures/mortgage | GET | 30 min | 25 min | 25 min | tab/filter UI
Mortgage Capture | Record detail | capture.mortgage.detail | /api/v1/captures/mortgage/:id | GET | 20 min | 25 min | 20 min | edit modal data
Mortgage Capture | Save draft | capture.mortgage.saveDraft | /api/v1/captures/mortgage/:id/draft | POST | 20 min | 25 min | 25 min | draft save
Mortgage Capture | Submit record | capture.mortgage.submit | /api/v1/captures/mortgage/:id/submit | POST | 25 min | 25 min | 25 min | submit flow
Mortgage Capture | Bulk approve | capture.mortgage.bulkApprove | /api/v1/captures/mortgage/bulk-approve | POST | 20 min | 25 min | 25 min | batch approve
Mortgage Capture | Bulk reject | capture.mortgage.bulkReject | /api/v1/captures/mortgage/bulk-reject | POST | 20 min | 25 min | 25 min | batch reject
Mortgage Capture | Audit history | capture.mortgage.auditHistory | /api/v1/captures/mortgage/:id/audit-history | GET | 20 min | 25 min | 25 min | change log
Mortgage Capture | Recalculate emissions | capture.mortgage.recalculate | /api/v1/captures/mortgage/:id/recalculate | POST | 15 min | 25 min | 20 min | formula logic
User Management | User list | users.list | /api/v1/users | GET | 20 min | 25 min | 20 min | search + filters
User Management | Invite user | users.invite | /api/v1/users/invite | POST | 20 min | 25 min | 20 min | create user + send invite
User Management | Update user | users.update | /api/v1/users/:id | PUT | 20 min | 25 min | 20 min | edit modal
User Management | Activate user | users.activate | /api/v1/users/:id/activate | POST | 10 min | 15 min | 10 min | status toggle
User Management | Deactivate user | users.deactivate | /api/v1/users/:id/deactivate | POST | 10 min | 15 min | 10 min | status toggle
User Management | Import users | users.import | /api/v1/users/import | POST | 15 min | 25 min | 15 min | CSV upload
Role Management | Role list | roles.list | /api/v1/roles | GET | 15 min | 20 min | 15 min | role cards
Role Management | Create role | roles.create | /api/v1/roles | POST | 20 min | 25 min | 20 min | new role form
Role Management | Update role | roles.update | /api/v1/roles/:id | PUT | 20 min | 25 min | 20 min | edit role
Role Management | Delete role | roles.delete | /api/v1/roles/:id | DELETE | 10 min | 15 min | 10 min | role removal
Role Management | Permissions matrix | roles.permissions.get | /api/v1/roles/:id/permissions | GET | 20 min | 25 min | 20 min | matrix load
Role Management | Save permissions | roles.permissions.update | /api/v1/roles/:id/permissions | PUT | 20 min | 25 min | 20 min | matrix persist
Settings | Load settings | settings.get | /api/v1/settings | GET | 15 min | 20 min | 15 min | initial load
Settings | Organisation profile | settings.organisation.update | /api/v1/settings/organisation | PUT | 20 min | 25 min | 20 min | profile save
Settings | Reporting config | settings.reporting.update | /api/v1/settings/reporting | PUT | 20 min | 25 min | 20 min | currency/FY config
Settings | Notifications | settings.notifications.update | /api/v1/settings/notifications | PUT | 20 min | 25 min | 20 min | toggle save
Settings | Integrations list | settings.integrations.list | /api/v1/settings/integrations | GET | 15 min | 20 min | 15 min | integration status
Settings | Connect integration | settings.integrations.connect | /api/v1/settings/integrations/:id/connect | POST | 15 min | 25 min | 20 min | external connect

## Sheet2
Table | Purpose
users | platform users, roles, status, last login
roles | role master data
role_permissions | module-wise permissions for roles
settings | organisation and reporting configuration
settings_notifications | notification preferences
integrations | external integration status/config
loan_configs_business | business loan master/config data
loan_configs_cre | commercial real estate master/config data
loan_configs_motor_vehicle | motor vehicle master/config data
loan_configs_mortgage | mortgage master/config data
capture_business_loans | business loan capture records
capture_cre | commercial real estate capture records
capture_motor_vehicle | motor vehicle capture records
capture_mortgage | mortgage capture records
audit_logs | history of changes, approvals, rejects, edits
dashboard_snapshots | cached aggregates if needed for speed